## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Rashid |  | 2. Save to one team member's Google drive
Abdullah |  | 3. Share file with other team members
Khalid |  | 4. Edit First Names on this tab
Mohammed |  | 5. Add your team name to the name of this document
6. For each sprint, duplicate the sprint template and change the start date
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
3 | S1 | Destination Details | As a traveler, I want detailed information on tourist attractions, including points of interest and accommodations, so that I can plan my trips effectively | The app should allow sorting by categories like historical sites, natural spots, or museums, making it easy to find exactly what I want. | 1-high | Done
3 | S2 | Travel Schedule Planning | As a user, I want to create personalized travel plans based on my preferences and available time so that my trips are tailored to my interests | Saving, editing, and organizing plans should be simple, and setting reminders for my visits would be very helpful. | 1-high | Done
3 | S3 | Live Updates and GPS Maps | As a traveler, I want real-time updates on weather and events, along with GPS-enabled maps, so that I can navigate and adjust my plans easily | It would be useful to choose specific types of updates, like only weather or events, and use maps with clear routes and points of interest | 1-high | Done
3 | S4 | Booking Accommodations | As a user, I want to find and book accommodations like hotels or rentals through the app so that I can make planning my trips easier | Filters for price and location would make it easier to find the right place, with booking confirmations sent directly in the app | 2-medium | Done
3 | S5 | Transportation and Booking Options | As a traveler, I want access to various transportation options, like public transit and car rentals, so that I can book them easily and travel without hassle | The app should show updated schedules and allow direct bookings to simplify my travel arrangements | 2-medium | Done
2 | S6 | Data Security and Privacy | As a user, I want my personal data to be secure and private so that I can use the app with confidence | The app should have strong security measures, like encryption, and give me control over my privacy settings | 1-high | Done
3 | S7 | Offline Capabilities | As a user, I want to access essential features like maps and saved itineraries offline so that I’m not stuck without information when I lose internet access | Key data should be stored on the device, with updates syncing when back online | 2-medium | Done
3 | S8 | Multi-Platform Compatibility | As a user, I want the app to work well across all my devices, including phones and tablets, so that I have a consistent experience no matter what I use | should adapt to various screen sizes and work smoothly on both iOS and Android | 2-medium | Done
1 | S9 | User Account Management | As a user, I want to easily create and manage my account so that I can keep track of my saved preferences and plans | The app should offer easy options for account setup, login, and managing personal info | 3-low | Done
3 | S10 | Feedback and Support | As a user, I want to be able to give feedback and get help when I need it so that I can resolve any issues or get answers to my questions quickly | A feedback form and a support section with FAQs or contact options would be ideal | 3-low | Done

## Sprint 1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| Project Initiation | 1 | 1.5 | Rashid | Done | 2024-09-05 | Sprint Number: | 1 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-09-05 | 1 | 1 | 30 | 31
| Product Backlog Description | 2 | 1 | Abdullah | Done | 2024-09-06 | Start Date: | 2024-09-05 | Rashid | 10 | 10 | 100% | 2024-09-06 | 2 | 3 | 28 | 27.9
| User and System Requirements | 3 | 4 | Khalid | Done | 2024-09-07 | Sprint Length | 10 | Abdullah | 8 | 8 | 100% | 2024-09-07 | 3 | 6 | 25 | 24.8
| Sprint planning | 3 | 2.5 | Mohammed | Done | 2024-09-08 | Hours Per Day: | 3.1 | Khalid | 7 | 7 | 100% | 2024-09-08 | 3 | 9 | 22 | 21.7
S9 | Start working on the front-end by creating a login screen for the user using HTML, JavaScript and CSS | 9 | 10 | Rashid | Done | 2024-09-12 |  |  | Mohammed | 6 | 6 | 100% | 2024-09-09 | 3 | 12 | 19 | 18.6
S9 | Start working on the front-end by creating a login screen for the user using HTML, JavaScript and CSS | 6 | 8 | Abdullah | Done | 2024-09-11 | [6 empty] | 2024-09-10 | 3 | 15 | 16 | 15.5
S9 | Begin to get familiar with Firebase and determine if it could work as a back-end frame work | 3 | 2 | Mohammed | Done | 2024-09-09 |  |  | Total: | 31 | 31 | 100% | 2024-09-11 | 6 | 21 | 10 | 12.4
| Start filling out the excel sheet and review the work with each member | 3 | 4 | Khalid | Done | 2024-09-10 | [6 empty] | 2024-09-12 | 9 | 30 | 1 | 9.3
| Review all the work and make sure everything is good to go before submission | 1 | 0.5 | Khalid | Done | 2024-09-13 | [6 empty] | 2024-09-13 | 1 | 31 | 0 | 6.2
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M8-[Current Completed Work], "")
Current Remaining Work = IF([Chart Dates, row above] <= TODAY(), M8-[Current Completed Work], "")

## Sprint 2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
| Activity Diagram | 2 | 2 | Mohammed | Done | 2024-09-19 | Sprint Number: | 2 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-09-18 | 0 | 0 | 44 | 44
| Use Case Diagram | 8 | 10 | Mohammed | Done | 2024-09-24 | Start Date: | 2024-09-18 | Rashid | 13 | 13 | 100% | 2024-09-19 | 2 | 2 | 42 | 40.6154
| Class Diagram | 3 | 4 | Khalid | Done | 2024-09-20 | Sprint Length | 13 | Abdullah | 12 | 12 | 100% | 2024-09-20 | 3 | 5 | 39 | 37.2308
| MVC pattern diagram | 4 | 5 | Khalid | Done | 2024-09-25 | Hours Per Day: | 3.3846 | Khalid | 9 | 9 | 100% | 2024-09-21 | 0 | 5 | 39 | 33.8462
S9 | Finish working on the login page and making sure it is ready for the next phase | 2 | 2 | Abdullah | Done | 2024-09-26 |  |  | Mohammed | 10 | 10 | 100% | 2024-09-22 | 0 | 5 | 39 | 30.4615
S9 | Testing login page functionality and integrating it with the Home Page | 1 | 1 | Rashid | Done | 2024-09-26 | [6 empty] | 2024-09-23 | 0 | 5 | 39 | 27.0769
| Designing the Home Page | 3 | 2 | Rashid | Done | 2024-09-27 |  |  | Total: | 44 | 44 | 100% | 2024-09-24 | 8 | 13 | 31 | 23.6923
| Coding the Home Page | 8 | 12 | Rashid | Done | 2024-09-28 | [6 empty] | 2024-09-25 | 4 | 17 | 27 | 20.3077
| Coding the Home Page | 7 | 11 | Abdullah | Done | 2024-09-28 | [6 empty] | 2024-09-26 | 3 | 20 | 24 | 16.9231
S6 | Find out industry standard for security and integrity to be used in the project | 2 | 2 | Abdullah | Done | 2024-09-29 | [6 empty] | 2024-09-27 | 3 | 23 | 21 | 13.5385
| Testing the Home Page functionality and integrity | 1 | 2 | Abdullah | Done | 2024-09-30 | [6 empty] | 2024-09-28 | 15 | 38 | 6 | 10.1538
| Fill out the excel sheet and review the work with each member | 2 | 1 | Khalid | Done | 2024-10-01 | [6 empty] | 2024-09-29 | 2 | 40 | 4 | 6.7692
| Review all the work and make sure everything is good to go before submission | 1 | 1 | Rashid | Done | 2024-10-01 | [6 empty] | 2024-09-30 | 1 | 41 | 3 | 3.3846
[13 empty] | 2024-10-01 | 3 | 44 | 0 | 0
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M8-[Current Completed Work], "")
Current Remaining Work = IF([Chart Dates, row above] <= TODAY(), M8-[Current Completed Work], "")

## Sprint 3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Add a tab to show details for the selected destination | 4 | 4 | Rashid | Done | 2024-10-07 | Sprint Number: | 3 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2024-10-07 | 8 | 8 | 30.5 | 38.5
S2 | Create a page where the users can plan their travel schedules | 4 | 5 | Abdullah | Done | 2024-10-07 | Start Date: | 2024-10-07 | Rashid | 14.5 | 14.5 | 100% | 2024-10-08 | 4 | 12 | 26.5 | 35.2917
S3 | Provide live updates and GPS maps using APIs | 4 | 5 | Abdullah | Done | 2024-10-08 | Sprint Length | 12 | Abdullah | 14 | 14 | 100% | 2024-10-09 | 3 | 15 | 23.5 | 32.0833
S4 | Add the option to book accomodations | 3 | 4 | Rashid | Done | 2024-10-09 | Hours Per Day: | 3.2083 | Khalid | 6 | 6 | 100% | 2024-10-10 | 3.5 | 18.5 | 20 | 28.875
S5 | Add options for booking and transportation | 3.5 | 3 | Rashid | Done | 2024-10-10 |  |  | Mohammed | 4 | 4 | 100% | 2024-10-11 | 3 | 21.5 | 17 | 25.6667
S7 | Make the website secure and protect user data by applying industry standards | 3 | 3 | Abdullah | Done | 2024-10-11 | [6 empty] | 2024-10-12 | 0 | 21.5 | 17 | 22.4583
S8 | Make the website compatable with various platforms | 4 | 5 | Rashid | Done | 2024-10-14 |  |  | Total: | 38.5 | 38.5 | 100% | 2024-10-13 | 0 | 21.5 | 17 | 19.25
S10 | Provide a tab for user feedback | 3 | 3 | Abdullah | Done | 2024-10-15 | [6 empty] | 2024-10-14 | 4 | 25.5 | 13 | 16.0417
| Make the PowerPoint presentation | 4 | 4.5 | Khalid | Done | 2024-10-16 | [6 empty] | 2024-10-15 | 3 | 28.5 | 10 | 12.8333
| Review all the work and make sure everything is good to go before submission | 4 | 3 | Mohammed | Done | 2024-10-17 | [6 empty] | 2024-10-16 | 4 | 32.5 | 6 | 9.625
| Fill out the excel sheet | 2 | 1 | Khalid | Done | 2024-10-18 | [6 empty] | 2024-10-17 | 4 | 36.5 | 2 | 6.4167
[13 empty] | 2024-10-18 | 0 | 36.5 | 2 | 3.2083
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M8-[Current Completed Work], "")
Current Remaining Work = IF([Chart Dates, row above] <= TODAY(), M8-[Current Completed Work], "")